## Sheet1
Change Management Approach for AI enabled Organisation
Kotter's 8-Step Framework
| ACTIVITIES | Make Your Plans | Set Time-lines
Step 1: Create Urgency
| Identify potential threats , and develop scenarios showing what could happen in the future. | Objective: Inspire stakeholders to recognize the need for change.
| Examine opportunities that should be, or could be, exploited. | · Conduct a comprehensive analysis highlighting market trends, customer demands, and competitive threats. | 3 weeks
| Start honest discussions, and give dynamic and convincing reasons to get people talking and thinking. | · Share key data points on declining customer satisfaction and operational inefficiencies. | 2 weeks
| Request support from customers, outside stakeholders and industry people to strengthen your argument. | · Organize town hall meetings, workshops, and awareness campaigns to communicate the urgency. | 2-4 weeks
|  | · Identify and address potential resistance points early. | OnGoing
Key Deliverable: Compelling case for change with data-driven insights.
Step 2: Form a Powerful Coalition | ACTIVITIES | Make Your Plans | Set Time-lines
| Identify the true leaders in your organization, as well as your key stakeholders . | Objective: Form a powerful team to lead the change. | 2 weeks
| Ask for an emotional commitment from these key people. | · Identify influential leaders across departments (executive sponsors, team leads, technical experts). | Ongoing
| Work on team building within your change coalition. | · Form a cross-functional change leadership team with clear roles and responsibilities. | Ongoing
| Check your team for weak areas, and ensure that you have a good mix of people from different departments and different levels within your company. | · Develop a charter that defines the coalition’s mission and authority. | 2 weeks
Key Deliverable: Established coalition with defined objectives and accountability.
Step 3: Create a Vision for Change | ACTIVITIES | Make Your Plans | Set Time-lines
| Determine the values that are central to the change. | Objective: Create a clear vision that aligns with organizational goals. | 2 weeks
| Develop a short summary (one or two sentences) that captures what you "see" as the future of your organization. | · Define a clear and concise vision statement for the change initiative. | 1 week
| Create a strategy to execute that vision. | · Establish strategic objectives that focus on customer experience enhancement and operational improvements. | 2 weeks
| Ensure that your change coalition can describe the vision in five minutes or less. | · Develop a roadmap with milestones, timelines, and key performance indicators (KPIs). | 1 week
| Practice your "vision speech" often. | Key Deliverable: Documented vision, strategy, and roadmap. | 1 week
Step 4: Communicate the Vision | ACTIVITIES | Make Your Plans | Set Time-lines
| Talk often about your change vision. | Objective: Embed the new practices into the organization's culture. | 2 weeks
| Address peoples' concerns and anxieties, openly and honestly. | · Align policies, reward systems, and performance evaluations with new behaviors. | 1 week
| Apply your vision to all aspects of operations – from training to performance reviews. Tie everything back to the vision. | · Encourage leaders to model and reinforce the new culture. | 1 week
| Lead by example . | · Develop long-term training programs to sustain skills and adoption. | 2 weeks
Key Deliverable: Institutionalized change embedded in the organization’s DNA.
Step 5: Remove Obstacles | ACTIVITIES | Make Your Plans | Set Time-lines
| Identify, or hire, change leaders whose main roles are to deliver the change. | Objective: Remove obstacles and encourage innovative thinking. | Ongoing
| Look at your organizational structure, job descriptions, and performance and compensation systems to ensure they're in line with your vision. | · Identify and eliminate barriers such as outdated processes or limited resources. | Ongoing
| Recognize and reward people for making change happen. | · Provide training programs to upskill employees for new digital tools. | Ongoing
| Identify people who are resisting the change, and help them see what's needed. | · Recognize and support change agents who champion the new direction. | Ongoing
| Take action to quickly remove barriers (human or otherwise). | Key Deliverable: Empowered employees with the tools and knowledge to drive change.
Step 6: Create Short-Term Wins | ACTIVITIES | Make Your Plans | Set Time-lines
| Look for sure-fire projects that you can implement without help from any strong critics of the change. | Objective: Deliver immediate successes to build momentum. | 1 week
| Don't choose early targets that are expensive. You want to be able to justify the investment in each project. | · Identify achievable goals that align with the overall transformation strategy. | 1 week
| Thoroughly analyze the potential pros and cons of your targets. If you don't succeed with an early goal, it can hurt your entire change initiative. | · Celebrate early wins publicly to reinforce progress and encourage continued efforts. | ongoing
| Reward the people who help you meet the targets. | · Track KPIs to highlight measurable improvements. | ongoing
Key Deliverable: Documented successes with visible impact.
Step 7: Build on the Change | ACTIVITIES | Make Your Plans | Set Time-lines
| After every win, analyze what went right, and what needs improving. | Objective: Maintain momentum by building on early successes. | Ongoing
| Set goals to continue building on the momentum you've achieved. | · Continuously refine strategies based on lessons learned. | Ongoing
| Learn about kaizen , the idea of continuous improvement. | · Expand the change initiative into new departments or processes. | Ongoing
| Keep ideas fresh by bringing in new change agents and leaders for your change coalition. | · Regularly assess progress against KPIs and adjust as needed. | Ongoing
Key Deliverable: Expanded implementation plan ensuring continuous improvement.
Step 8: Anchor the Changes in Corporate Culture | ACTIVITIES | Make Your Plans | Set Time-lines
| Talk about progress every chance you get. Tell success stories about the change process, and repeat other stories that you hear. | Objective: Embed the new practices into the organization's culture. | Ongoing
| Include the change ideals and values when hiring and training new staff. | · Align policies, reward systems, and performance evaluations with new behaviors. | Ongoing
| Publicly recognize key members of your original change coalition, and make sure the rest of the staff – new and old – remembers their contributions. | · Encourage leaders to model and reinforce the new culture. | Ongoing
| Create plans to replace key leaders of change as they move on. This will help ensure that their legacy is not lost or forgotten. | · Develop long-term training programs to sustain skills and adoption. | Ongoing
Key Deliverable: Institutionalized change embedded in the organization’s DNA.